## Product_Backlog
Product Name:	Robot Management System
Team ID:	SAM

Name:	simranjit singh ahluwalia
Initials:	SA
Student ID:	1000976594

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	18
Sprint 1 Left	18
Sprint 2 Left	17
Sprint 3 Left	14

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Sprint #	As a...	I want to...	So that...	Notes
	1			PM	create robot parts	I can define robot models	No menu required here – run program, create a part
	2			PM	define new robot models	RRS can sell them to our Beloved Customers	Menu needed – create parts, then create a robot model
	3			BC	browse a catalog of robots	I can buy one or more robots	Need to list robots models, then list parts in selected model
	4			SA	create a robot order for a Customer	I can sell robots and thus do my job well	Select robot model and quantity, show details with total price
	5			PB	ensure persistence of the RRS data	we don't lose orders or historical data	Write the data to disk and reload it next time the program runs
	6			PB / SA	view a list of orders per SA	I can estimate the value of employees / / I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
	7			BC	view my orders	see what I have coming to me	Show list of orders for a BC with total price, then list details of selected order
	8			BC	view my bill	I can pay for my robots	Show a BC invoice. Actual payment is outside the scope of this project
	9			SA	view a sales report	I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
	10			PB	view a list of orders	I can manage the company	Show list of every order with total price, then list details of selected order
	11			SA	create a bulk (2+) robot order for a Customer	avoid proliferation of orders and paperwork	Allow more than one robot model (with respective quantity) on a single order
	12			PM	hide robot parts	obsolete parts aren't accidentally used	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	13			PM	hide robot models	obsolete robots aren't ordered	Mark robot models as “obsolete” and don't allow adding them to new orders
	14			SA	save a draft order and return to it later	I can multi-task between indecisive customers	Save an order that hasn't been complete, and allow SA to resume work on it later
	15			PM	add custom pictures to robot models	BC are more likely to buy my robots	(Probably can't address until Homework #6)
	16			BC	see a pie chart of a model's component costs	I can decide if I want a different model	(Probably can't address until Homework #6)
	17			BC	browse and order robots over the web	I don't have to talk to the Sales Associates!	(Probably can't address until Homework #6)
	18			PB	avoid any delays in the RRS web software	my SA team is at maximum productivity	This likely means using threads for key processes / (Probably can't address until Homework #6)
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_NN_Backlog
Sprint #1
Start on	9/30/16 12:00 AM
End on	10/5/16 12:00 AM
Demo on

Total Tasks	18
Day 1 Left	18
Day 2 Left	18
Day 3 Left	18
Day 4 Left	18
Day 5 Left	18
Day 6 Left	18
Day 7 Left	18

Task ID	Feature ID	Category	Assigned To	Description	Status	Notes
1	1	robot part uml	simranjit	uml created for robot part class	partially completed	Need this for the next part of this project
2	1	robot part class cpp cpde	simranjit	cpp code created for robot part	partially completed	Need this for the next part of this project
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog_2
Sprint #2
Start on	10/6/16 12:00 AM
End on	10/13/16 12:00 AM
Demo on

Total Tasks	18
Day 1 Left	18
Day 2 Left	18
Day 3 Left	18
Day 4 Left	18
Day 5 Left	18
Day 6 Left	18
Day 7 Left	17

Task ID	Feature ID	Category	Assigned To	Description	Status	Notes
1	1	robot part uml	simranjit	uml created for robot part class	partially completed	Need this for the next part of this project
2	1	robot part class cpp cpde	simranjit	cpp code created for robot part	partially completed	Need this for the next part of this project
3	1	completed feature 1	simranjit	cpp code and uml created	completed
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog_3
Sprint #3
Start on	10/14/16 12:00 AM
End on	10/20/16 12:00 AM
Demo on

Total Tasks	17
Day 1 Left	17
Day 2 Left	17
Day 3 Left	17
Day 4 Left	17
Day 5 Left	15
Day 6 Left	14
Day 7 Left	14

Task ID	Feature ID	Category	Assigned To	Description	Status	Notes
1	1	robot part uml	simranjit	uml created for robot part class	partially completed	Need this for the next part of this project
2	1	robot part class cpp cpde	simranjit	cpp code created for robot part	partially completed	Need this for the next part of this project
3	1	completed feature 1	simranjit	cpp code and uml created	completed	N/A
4	2	create robot models	simranjit	model defined from the parts created	completed	A complete robot model is entered in the system
5	3	browse the robot models	simranjit	able to look all the models in the system	completed	customer can make decission about the choice of robot models
6	3	display details	simranjit	able to select the robot model of a choice	completed	customer can make decission by looking model in details
7	4	checkout the models	simranjit	customer can buy robot model	completed	customer can buy model of his or her choice
8	4	update the status	simranjit	sold robot should get updated in the system	completed	customer can look for the availability of a model
9	4	check record	simranjit	record purchasing history	completed	sales assocites/product manager can keep track of business
Sprint Burn Chart
Days
Tasks